## Project Detailed Task Plan
NyayaMitra AI - Team Member Task Map & Implementation Checklist
4 Members ¦ 4 Days ¦ Detailed Coding Deliverables & Execution Instructions
Part | Owner | Task Name | Priority | Target Day | Target Files | Task Description | Implementation Instructions
Part 1: Backend | Member 1 (Backend Dev) | FastAPI Skeleton Setup | Highest | Day 1 | backend/main.py, backend/config.py, backend/schemas.py | Create FastAPI app routing structures, unified JSON API responses, CORS configurations, and error middleware. | Ensure CORS is configured for http://localhost:3000 to avoid browser security blocks. Define core schemas for upload payload validation.
Part 1: Backend | Member 1 (Backend Dev) | Legal Knowledge Base JSON | High | Day 2 | backend/data/laws_kb.json | Compile primary civil laws (Transfer of Property Act Sec 106, Consumer Protection Act, BNS/IPC default notices) into structured JSON data. | Create standard fields for Law Title, Section ID, Legal Terms, Plain-English Translation, and General Citizen Recommendations.
Part 1: Backend | Member 1 (Backend Dev) | RAG Vector Index Service | High | Day 2 | backend/services/rag_retriever.py | Develop keyword and embedding-based search retrieval system mapping uploaded notice queries to matching laws_kb sections. | Use in-memory searching (TF-IDF or numpy cosine-similarity) to prevent SQLite/C++ wheel build errors on Windows/Python 3.14.
Part 1: Backend | Member 1 (Backend Dev) | Chat API Router & Memory | Medium | Day 3 | backend/routers/chat.py, backend/services/chat_manager.py | Build `/api/chat` route carrying conversation memory state for contextual follow-up document Q&A. | Implement dynamic conversation memory dictionary. Prevent memory bleeding across different documents by clearing states on new file uploads.
Part 1: Backend | Member 1 (Backend Dev) | Calendar Exporter & Template | Low | Day 4 | backend/services/calendar_generator.py | Code backend helper utility outputting dynamic schedule reminder calendar invite files (.ics) and formatted response draft templates. | Set timezone dynamically to local Indian Standard Time (IST) on calendar event generation. Verify file triggers immediate download in browser.
Part 2: Frontend | Member 2 (Frontend Dev) | Vite-React App Setup | Highest | Day 1 | frontend/package.json, frontend/src/App.tsx, frontend/src/index.css | Initialize React Vite project environment, global layouts, and design system variables (Navy, Amber, Slate). | Set core CSS styling color tokens. Code the primary app workspace frame (sidebar, main header toggle, workspace grid).
Part 2: Frontend | Member 2 (Frontend Dev) | File Drag-and-Drop View | Highest | Day 2 | frontend/src/components/UploadZone.tsx | Create drag-and-drop file upload container supporting PDF, PNG, and JPEG uploads. | Implement visual drop zone border changes on hover, handle file type validation, and wire it up to POST multipart `/api/upload`.
Part 2: Frontend | Member 2 (Frontend Dev) | Dual-Pane Layout Shell | High | Day 2 | frontend/src/components/WorkspaceLayout.tsx, DocViewer.tsx | Create the split-screen view: left pane renders PDF document preview; right pane loads the interactive tab panels. | Ensure pane dividers allow clean scrolling. Preview pane must load uploaded file locally using URL.createObjectURL.
Part 2: Frontend | Member 2 (Frontend Dev) | Notice Timeline & Alert Banner | High | Day 3 | frontend/src/components/TimelineWidget.tsx | Build a vertical milestone timeline highlighting critical notice dates and warning badges indicating remaining response days. | Generate active countdown variables (e.g. '3 Days Remaining'). Color-code deadlines: High (Red), Medium (Orange), Low (Yellow).
Part 2: Frontend | Member 2 (Frontend Dev) | Mitra Checklist & Chat Panels | Medium | Day 3 | frontend/src/components/ChecklistWidget.tsx, ChatPanel.tsx | Code checklist items, download response template interface, and the sidebar interactive chat dialog box. | Add placeholder chat bubble arrays. Hook chat inputs to backend POST `/api/chat` and show load skeletons during responses.
Part 2: Frontend | Member 2 (Frontend Dev) | UI Polish & Transitions | Medium | Day 4 | frontend/src/index.css, frontend/src/components/UIElements.tsx | Refine visual design layers, add card hover glow transitions, check layouts across screen widths, and connect translation language hooks. | Refine glassmorphism drop-shadows. Ensure clicking Telugu button immediately triggers state translate changes throughout the page.
Part 3: AI Engine | Member 3 (AI Dev) | Gemini Client Wrapper | Highest | Day 1 | backend/services/gemini_client.py | Create helper client initializing connection to Gemini API safely using key from system variables. | Utilize google-generativeai SDK. Ensure the key is fetched safely from `os.getenv('GEMINI_API_KEY')` without exposing raw values.
Part 3: AI Engine | Member 3 (AI Dev) | Uploader Ingest Connect API | Highest | Day 1 | backend/routers/upload.py | Connect uploader endpoints to Gemini multimodal model parser to extract text and structure from raw images/PDFs. | Send the file directly as prompt attachment. Instruct model to output clean text, classification type, and date references.
Part 3: AI Engine | Member 3 (AI Dev) | Structured Synthesis Engine | High | Day 2 | backend/services/analysis_synthesizer.py | Implement Pydantic verification structures ensuring LLM outputs summaries, dates, citations, and checklists in valid JSON format. | Configure strict schema parameters on Gemini. If formatting errors happen, construct retry loops to fix JSON string output.
Part 3: AI Engine | Member 3 (AI Dev) | Contextual Prompt Orchestrator | Medium | Day 3 | backend/services/chat_synthesizer.py | Design prompt frameworks combining active document contents, RAG database sections, and user query logs for chat reply rendering. | Ground chat facts solely in RAG legal rules. Force the LLM to output an informational disclaimer banner statement on queries.
Part 3: AI Engine | Member 3 (AI Dev) | Bilingual Translator Pipeline | Medium | Day 3/4 | backend/services/translator.py | Construct backend translation utility mapping generated summary analysis and timelines to Telugu using Gemini. | Ensure dates, names, and markup codes (like list points) are preserved exactly during conversion to Telugu.
Part 4: QA & Present | Member 4 (QA/Accessibility) | Mock Document Generation | Highest | Day 1 | backend/data/sample_eviction_notice.png, sample_summons.pdf | Create realistic mock notice assets (eviction summons, credit repayment letters) in image and PDF formats. | Notice texts should contain specific dates (like 'reply within 15 days'), names, and citations to test parser pipelines.
Part 4: QA & Present | Member 4 (QA/Accessibility) | Backend API Verification | High | Day 2 | backend/tests/test_api.py | Develop automated python test suites using `pytest` validating API endpoints, Gemini parsers, and vector matching results. | Run validation using mock notices: `pytest backend/tests/`. Ensure all tests complete without throwing errors.
Part 4: QA & Present | Member 4 (QA/Accessibility) | Browser TTS Speech Widget | High | Day 4 | frontend/src/components/VoiceReader.tsx | Build React widget accessing browser Web Speech API for reading summaries aloud in English and Telugu. | Add speech controls: Play, Pause, Stop, Voice Selection, and Speed slider. Validate Telugu voice engine compatibility.
Part 4: QA & Present | Member 4 (QA/Accessibility) | WhatsApp Notification Mockup | Low | Day 3/4 | backend/services/sms_scheduler_mock.py | Write mock backend service showing simulated automated SMS and WhatsApp reminders as notice deadlines get close. | Trigger alert pings on terminal logs when mock scheduler is running, simulating twilio message responses.
Part 4: QA & Present | Member 4 (QA/Accessibility) | Presentation slides & Demo Package | High | Day 4 | README.md, presentation_guide.md | Write local setup instructions inside README.md, outline IEEE hackathon slides, and capture backup walkthrough video screen captures. | Focus presentation elements around societal impact, digital inclusion, and Python 3.14 environment code optimization.