## Project Tasks Plan
NyayaMitra AI - Project Sprint Work Allocation
4-Member Team / 4-Day Roadmap ¦ Target Location: C:\Users\hansh\Downloads\IEEE
Part | Owner | Task Name | Description | Priority | Target Files to Include / Modify | Target Day
Part 1: Backend & Database | Member 1 (Backend Dev) | FastAPI Skeleton Setup | Setup routing structures, custom error middleware, CORS config, response schemas. | Highest | backend/main.py, backend/config.py, backend/schemas.py | Day 1
Part 1: Backend & Database | Member 1 (Backend Dev) | Legal Knowledge Base JSON | Compile primary civil laws, consumer codes, landlord tenant notice templates in structured file. | High | backend/data/laws_kb.json | Day 2
Part 1: Backend & Database | Member 1 (Backend Dev) | RAG Vector Index Service | Implement cosine-similarity query index logic inside the search retriever. | High | backend/services/rag_retriever.py | Day 2
Part 1: Backend & Database | Member 1 (Backend Dev) | Chat API Router & Memory | Build chat endpoints supporting active context storage of document history. | Medium | backend/routers/chat.py, backend/services/chat_manager.py | Day 3
Part 1: Backend & Database | Member 1 (Backend Dev) | Calendar Event Exporter | Setup backend module generating custom ICS schedule event files on query. | Low | backend/services/calendar_generator.py | Day 4
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | Vite-React App Setup | Setup React layout, navigation sidebar, Tailwind styles configurations. | Highest | frontend/package.json, frontend/src/App.tsx, frontend/src/index.css | Day 1
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | File Drag-and-Drop View | Build upload components showing file progress, sizes, and file type validation. | Highest | frontend/src/components/UploadZone.tsx | Day 2
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | Dual-Pane Layout Shell | Implement side-by-side workspace displaying uploaded file preview beside active analysis. | High | frontend/src/components/WorkspaceLayout.tsx, DocViewer.tsx | Day 2
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | Notice Timeline & Alert | Create visual milestones listing notice action deadlines and remaining days countdown badges. | High | frontend/src/components/TimelineWidget.tsx | Day 3
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | Mitra Checklist & Chat Panels | Design checklist panels with progress checkboxes and chatbot message history. | Medium | frontend/src/components/ChecklistWidget.tsx, ChatPanel.tsx | Day 3
Part 2: UI Workspace Layout | Member 2 (Frontend Dev) | CSS Polish & Animations | Apply micro-animations on interactive cards, hover elements, glassmorphism templates. | Medium | frontend/src/index.css, frontend/src/components/UIElements.tsx | Day 4
Part 3: AI Engine & Pipelines | Member 3 (AI Dev) | Gemini Client Integration | Build basic API query wrapper managing Gemini model execution. | Highest | backend/services/gemini_client.py | Day 1
Part 3: AI Engine & Pipelines | Member 3 (AI Dev) | Uploader Ingestion Connect | Connect backend uploader routing to execute multimodal page content extraction via Gemini. | Highest | backend/routers/upload.py | Day 1
Part 3: AI Engine & Pipelines | Member 3 (AI Dev) | Structured Synthesis Engine | Force Gemini to parse summary content and dates inside strict validation models (JSON schema). | High | backend/services/analysis_synthesizer.py | Day 2
Part 3: AI Engine & Pipelines | Member 3 (AI Dev) | Contextual Prompt Orchestrator | Construct prompt chains feeding extracted notice sections and laws to chat assistant. | Medium | backend/services/chat_synthesizer.py | Day 3
Part 3: AI Engine & Pipelines | Member 3 (AI Dev) | Bilingual Translator Pipeline | Build translation pipeline API to map summaries and instructions to Telugu using Gemini. | Medium | backend/services/translator.py | Day 3/4
Part 4: Quality & Accessibility | Member 4 (QA/Accessibility) | Mock Document Generation | Generate mock eviction notices and consumer default documents for demo pipeline testing. | Highest | backend/data/sample_eviction_notice.png, sample_summons.pdf | Day 1
Part 4: Quality & Accessibility | Member 4 (QA/Accessibility) | Backend API Verification | Configure automated test pipeline testing OCR, classifier, and RAG matching endpoints. | High | backend/tests/test_api.py | Day 2
Part 4: Quality & Accessibility | Member 4 (QA/Accessibility) | Browser TTS Audio Controller | Implement native speech playback buttons supporting volume and speed control settings. | High | frontend/src/components/VoiceReader.tsx | Day 4
Part 4: Quality & Accessibility | Member 4 (QA/Accessibility) | WhatsApp Notification Mockup | Design visual flows showcasing SMS alerts and WhatsApp chatbot responses. | Low | backend/services/sms_scheduler_mock.py | Day 3/4
Part 4: Quality & Accessibility | Member 4 (QA/Accessibility) | Documentation & Rehearsal | Compile final README guide folders, slides visual materials, and check presentation runs. | High | README.md, presentation_guide.md | Day 4